## Financial Proj
Housing | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016
Projected Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | 45000 | 115000 | 467000 | 1520000 | 2470000 | 2850000
Quarterly Projection | 0 | [6 empty] | 0 | 14000 | 31000 | 70000 | 352000 | 1053000 | 950000 | 380000
Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Quarterly Expend (from QPRs) | 0
Non-Housing | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016
Projected Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2895000 | 4724600 | 5865000 | 7316000 | 8866000 | 9616000 | 10556000 | 10556000
Quarterly Projection | 0 | [6 empty] | 2895000 | 1829600 | 1140400 | 1451000 | 1550000 | 750000 | 940000
Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Quarterly Expend (from QPRs) | 0
Planning & Admin | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016
Projected Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 150000 | 200000 | 250000 | 325000 | 400000 | 450000 | 500000
Quarterly Projection | 0 | [6 empty] | 75000 | 75000 | 50000 | 50000 | 75000 | 75000 | 50000 | 50000
Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Quarterly Expend (from QPRs) | 0
Total Expenditures | 7/2012 | 10/2012 | 1/2013 | 4/2013 | 7/2013 | 10/2013 | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016
Projected Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2970000 | 4888600 | 6110000 | 7681000 | 9658000 | 11536000 | 13476000 | 13906000
Quarterly Projection | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2970000 | 1918600 | 1221400 | 1571000 | 1977000 | 1878000 | 1940000 | 430000
Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Quarterly Expend (from QPRs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Performance Proj - Page 1
Construction of New Housing | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016
Projected Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 7
# of Housing Units (Quarterly Projection) | [7 empty] | 4 | 3
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Housing Units (Populated from QPR Reporting)
Demolition | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016
Structures | 0 | 0 | 2 | 6 | 8 | 10 | 12 | 12 | 12
# of Structures Demolished (Quarterly Projection) |  |  | 2 | 4 | 2 | 2 | 2
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Structures Demolished (Populated from QPR Reporting)
Residential Rehab and Reconstruction | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016
Projected Units | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 12 | 14
# of Housing Units (Quarterly Projection) | [6 empty] | 4 | 8 | 2
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Housing Units (Populated from QPR Reporting)
Public Facilities | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016
Projected Facilities | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
# of Public Facilities (Quarterly Projection) | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
Actual Facilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Public Facilities (Populated from QPR Reporting)
Quarterly Projections by Activity Type:
Acquisition, construction,reconstruction of public facilities
# of Public Facilities | [5 empty] | 1
Construction/reconstruction of water lift stations
# of Public Facilities
Construction/reconstruction of water/sewer lines or systems
# of Public Facilities
Dike/dam/stream-river bank repairs
# of Public Facilities
Rehabilitation/reconstruction of public facilities
# of Public Facilities
Public Service - Job Training | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016
Job Training | 0 | 0 | 0 | 25 | 50 | 100 | 100 | 100 | 100
# of people trained (Quarterly Projection) | 0 | 0 | 0 | 25 | 25 | 50 | 0 | 0 | 0
Training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Jobs Created/Retained (Populated from QPR Reporting)
# of Permanent Jobs Created
# of Permanent Jobs Retained
Public Infrastructure | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016
Projected Linear Feet of Public Improvements | 0 | 0 | 15000 | 45000 | 56000 | 56000 | 56000 | 56000 | 56000
# of Linear Feet of Public Improvements (Quarterly Projection) | 0 | 0 | 15000 | 30000 | 11000 | 0 | 0 | 0 | 0
Actual Linear Feet of Public Improvements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Linear Feet of Public Improvements (Populated from QPR Reporting)
Quarterly Projections by Activity Type:
Construction/reconstruction of water/sewer lines or systems
# of Linear Feet of Public Improvements
Dike/dam/stream-river bank repairs
# of Linear Feet of Public Improvements
Rehabilitation/reconstruction of a public improvement
# of Linear Feet of Public Improvements

## Performance Proj - Page 2
Economic Development | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016
Business Assisted | 0 | 0 | 0 | 3 | 6 | 9 | 10 | 10 | 10
# of Business Assisted (Quarterly Projection) |  |  |  | 3 | 3 | 3 | 1 | 0 | 0
Actual Businesses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Businesses Assisted (Populated from QPR Reporting)
Acquisition | 1/2014 | 4/2014 | 7/2014 | 10/2014 | 1/2015 | 4/2015 | 7/2015 | 10/2015 | 1/2016
Properties | 0 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2
# of Properties Acquired (Quarterly Projection) |  | 1 | 1 | 0 | 0 | 0 | 0 | 0
Actual Properties Acquired | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Properties Acquired (Populated from QPR Reporting)