## Financial Proj
Housing | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022 | 10/2022 | 1/2023 | 4/2023 | 7/2023 | 10/2023 | 1/2024 | 4/2024
Projected Expenditures | 25000 | 50001 | 150001 | 350001 | 550001 | 800001 | 950001 | 1100001 | 1500001 | 1900001 | 2300001 | 2550001 | 3050001 | 3550001 | 3950001 | 4150001 | 4400001 | 4475001 | 4550001 | 4625001 | 4675001 | 4675001 | 4675001 | 4675001 | 4675001 | 4675001 | 4675001 | 4675001
Quarterly Projection | 25000 | 25001 | 100000 | 200000 | 200000 | 250000 | 150000 | 150000 | 400000 | 400000 | 400000 | 250000 | 500000 | 500000 | 400000 | 200000 | 250000 | 75000 | 75000 | 75000 | 50000
Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Quarterly Expend (from QPRs) | 0
Non-Housing | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022 | 10/2022 | 1/2023 | 4/2023 | 7/2023 | 10/2023 | 1/2024 | 4/2024
Projected Expenditures | 1555000 | 3735000 | 5525000 | 5815000 | 6105000 | 6366716 | 6516716 | 6666716 | 7166716 | 7666716 | 8166716 | 8666716 | 9166716 | 9666716 | 10166716 | 10516716 | 10616716 | 10716716 | 10766716 | 10816716 | 10859216 | 10859216 | 10859216 | 10859216 | 10859216 | 10859216 | 10859216 | 10859216
Quarterly Projection | 1555000 | 2180000 | 1790000 | 290000 | 290000 | 261716 | 150000 | 150000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 350000 | 100000 | 100000 | 50000 | 50000 | 42500
Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Quarterly Expend (from QPRs) | 0
Planning & Admin | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022 | 10/2022 | 1/2023 | 4/2023 | 7/2023 | 10/2023 | 1/2024 | 4/2024
Projected Expenditures | 196882 | 514545 | 674545 | 784545 | 889819 | 994819 | 1049819 | 1104819 | 1159819 | 1214819 | 1269819 | 1320819 | 1371819 | 1391819 | 1411819 | 1431819 | 1451819 | 1471819 | 1491819 | 1506819 | 1522663 | 1522663 | 1522663 | 1522663 | 1522663 | 1522663 | 1522663 | 1522663
Quarterly Projection | 196882 | 317663 | 160000 | 110000 | 105274 | 105000 | 55000 | 55000 | 55000 | 55000 | 55000 | 51000 | 51000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 15000 | 15844
Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Quarterly Expend (from QPRs) | 0
Total Expenditures | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022 | 10/2022 | 1/2023 | 4/2023 | 7/2023 | 10/2023 | 1/2024 | 4/2024
Projected Expenditures | 1776882 | 4299546 | 6349546 | 6949546 | 7544820 | 8161536 | 8516536 | 8871536 | 9826536 | 10781536 | 11736536 | 12537536 | 13588536 | 14608536 | 15528536 | 16098536 | 16468536 | 16663536 | 16808536 | 16948536 | 17056880 | 17056880 | 17056880 | 17056880 | 17056880 | 17056880 | 17056880 | 17056880
Quarterly Projection | 1776882 | 2522664 | 2050000 | 600000 | 595274 | 616716 | 355000 | 355000 | 955000 | 955000 | 955000 | 801000 | 1051000 | 1020000 | 920000 | 570000 | 370000 | 195000 | 145000 | 140000 | 108344 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Quarterly Expend (from QPRs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Performance Proj
Residential Rehab and Reconstruction | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022 | 10/2022 | 1/2023 | 4/2023 | 7/2023 | 10/2023 | 1/2024 | 4/2024
Projected Units | 0 | 0 | 0 | 2 | 4 | 9 | 15 | 21 | 27 | 33 | 43 | 53 | 63 | 68 | 73 | 78 | 83 | 88 | 93 | 98 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
# of Housing Units (Quarterly Projection) | 0 | 0 | 0 | 2 | 2 | 5 | 6 | 6 | 6 | 6 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2
Actual Units | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Housing Units (Populated from QPR Reporting) | 0
Public Facilities | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022 | 10/2022 | 1/2023 | 4/2023 | 7/2023 | 10/2023 | 1/2024 | 4/2024
Projected Facilities | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
# of Public Facilities (Quarterly Projection) | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Facilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Public Facilities (Populated from QPR Reporting) | 0
Quarterly Projections by Activity Type:
Acquisition, construction,reconstruction of public facilities
# of Public Facilities | 0
Construction/reconstruction of water lift stations
# of Public Facilities | 0
Construction/reconstruction of water/sewer lines or systems
# of Public Facilities | 0
Dike/dam/stream-river bank repairs
# of Public Facilities | 0
Rehabilitation/reconstruction of public facilities
# of Public Facilities | 0 |  |  | 1 | [16 empty] | 1
Economic Development | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022 | 10/2022 | 1/2023 | 4/2023 | 7/2023 | 10/2023 | 1/2024 | 4/2024
Projected Jobs | 0 | 0 | 10 | 20 | 35 | 55 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
# of Jobs Created/Retained (Quarterly Projection) | 0 | 0 | 10 | 10 | 15 | 20 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Jobs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Jobs Created/Retained (Populated from QPR Reporting) | 0
# of Permanent Jobs Created | 0 |  | 10 | 10 | 15 | 20 | 15 | 15 | 15
# of Permanent Jobs Retained | 0
OUTCOME VALUES
% Increase in Business Revenue | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022 | 10/2022 | 1/2023 | 4/2023 | 7/2023 | 10/2023 | 1/2024 | 4/2024
Projected Increase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
% of Increase (Quarterly Projection) | 0 | 0 | [10 empty] | 2 |  |  |  | 2 |  |  |  | 1
Actual Increase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% of Increase (Populated from QPR Reporting) | 0
% Reduction in Utility Costs | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022 | 10/2022 | 1/2023 | 4/2023 | 7/2023 | 10/2023 | 1/2024 | 4/2024
Projected Reduction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
% of Reduction (Quarterly Projection) | 0 | [7 empty] | 3 | [11 empty] | 2
Actual Reduction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% of Reduction (Populated from QPR Reporting) | 0
# of Climate Action Plans Completed | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022 | 10/2022 | 1/2023 | 4/2023 | 7/2023 | 10/2023 | 1/2024 | 4/2024
Projected Plans Completed | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
# Completed (Quarterly Projection) | 0 | 1 | [10 empty] | 0 |  |  |  | 0 |  |  |  | 0
Actual # Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# Completed (Populated from QPR Reporting) | 0
% Reduction in kWh Used | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022 | 10/2022 | 1/2023 | 4/2023 | 7/2023 | 10/2023 | 1/2024 | 4/2024
Projected Reduction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
% of Reduction (Quarterly Projection) | 0 | [7 empty] | 3 | [11 empty] | 2
Actual Reduction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% of Reduction (Populated from QPR Reporting) | 0
# of Mitigation Plans Completed | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022 | 10/2022 | 1/2023 | 4/2023 | 7/2023 | 10/2023 | 1/2024 | 4/2024
Projected Plans Completed | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
# Completed (Quarterly Projection) | 0 | 1 | [10 empty] | 0 |  |  |  | 0 |  |  |  | 0
Actual # Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# Completed (Populated from QPR Reporting) | 0
# of Residential Building Permits | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022 | 10/2022 | 1/2023 | 4/2023 | 7/2023 | 10/2023 | 1/2024 | 4/2024
Projected Permits Issued | 0 | 2 | 4 | 9 | 15 | 21 | 27 | 33 | 43 | 53 | 63 | 68 | 73 | 78 | 83 | 88 | 93 | 98 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
# Issued (Quarterly Projection) | 0 | 2 | 2 | 5 | 6 | 6 | 6 | 6 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 |  | 0
Actual # Issued | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# Issued (Populated from QPR Reporting) | 0
# of Healthy Homes Interventions | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022 | 10/2022 | 1/2023 | 4/2023 | 7/2023 | 10/2023 | 1/2024 | 4/2024
Projected Interventions | 0 | 2 | 4 | 8 | 12 | 18 | 24 | 30 | 36 | 42 | 48 | 54 | 60 | 66 | 71 | 76 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
# of Interventions (Quarterly Projection) | 0 | 2 | 2 | 4 | 4 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 4 | 0 | 0 |  | 0
Actual # of Interventions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Interventions (Populated from QPR Reporting) | 0
# of People Enrolled | 7/2017 | 10/2017 | 1/2018 | 4/2018 | 7/2018 | 10/2018 | 1/2019 | 4/2019 | 7/2019 | 10/2019 | 1/2020 | 4/2020 | 7/2020 | 10/2020 | 1/2021 | 4/2021 | 7/2021 | 10/2021 | 1/2022 | 4/2022 | 7/2022 | 10/2022 | 1/2023 | 4/2023 | 7/2023 | 10/2023 | 1/2024 | 4/2024
Projected Enrollment | 0 | 10 | 35 | 55 | 75 | 95 | 115 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127 | 127
# of Enrollments (Quarterly Projection) | 0 | 10 | 25 | 20 | 20 | 20 | 20 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual # of Enrollments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
# of Enrollments (Populated from QPR Reporting) | 0